## Sana Asgharpour
Name: Sana Asgharpour
Student ID: 40244364
git username:
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes

## Salvatore Bruzzese
Name: Salvatore Bruzzese
Student ID: 40112201
git username: sbruzz
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes
2025-09-09 | Team meeting | 2 hours | complete | Sprint 1 kickoff and planning
2025-09-10 | Environment setup | 2 hours | complete | Installed .NET 9.0 SDK and tools
2025-09-11 | Repository setup | 1.5 hours | incomplete | Cloned repo and reviewed project structure (Task.03)
2025-09-12 | Database modeling | 3 hours | incomplete | Created Ticket model with relationships (Task.11)
2025-09-13 | Database modeling | 2 hours | incomplete | Created SavedEvent model for calendar (Task.13)
2025-09-14 | Code review | 1 hour | complete | Reviewed User and Event models
2025-09-16 | Team meeting | 1.5 hours | complete | Mid-sprint check-in
2025-09-17 | Backend development | 5 hours | incomplete | Implemented login logic with BCrypt (Task.20)
2025-09-18 | Backend development | 3 hours | incomplete | Added password hashing on signup (Task.21)
2025-09-19 | Testing | 3 hours | incomplete | Tested authentication with all user roles (Task.20, Task.21)
2025-09-20 | Backend development | 4 hours | incomplete | Implemented signup logic for students (Task.21)
2025-09-21 | Bug fixing | 2 hours | incomplete | Fixed BCrypt work factor configuration (Task.20)
2025-09-24 | Team meeting | 2 hours | complete | Sprint 1 review and retrospective
2025-09-25 | Backend development | 3 hours | incomplete | Continued work on authentication system (Task.20, Task.21)
2025-09-26 | Testing | 2 hours | incomplete | Tested authentication with all user roles (Task.20, Task.21)
2025-09-27 | Backend development | 4 hours | incomplete | Bug fixes and code cleanup (Task.20, Task.21)
2025-09-28 | Testing | 2.5 hours | incomplete | End-to-end testing of authentication flow (Task.20, Task.21)
2025-09-29 | Documentation | 1.5 hours | complete | Added XML comments to Page Models

## Souleymane Camara
Name: Souleymane Camara
Student ID:40183807
git username: mistersuun
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes
2025-09-09 | Team meeting | 2 hours | complete | Sprint 1 kickoff and planning
2025-09-10 | Environment setup | 2 hours | complete | Installed .NET 9.0 SDK and Visual Studio Code
2025-09-11 | Repository setup | 1.5 hours | complete | Cloned repository and reviewed Razor Pages structure
2025-09-12 | Frontend development | 3 hours | incomplete | Created Index.cshtml home page (Task.24)
2025-09-13 | Frontend development | 3.5 hours | incomplete | Created Login.cshtml page (Task.18)
2025-09-14 | CSS styling | 2.5 hours | incomplete | Applied initial styling to home and login pages (Task.24, Task.18)
2025-09-16 | Team meeting | 1.5 hours | complete | Mid-sprint check-in
2025-09-17 | Page models | 3.5 hours | incomplete | Implemented Login.cshtml.cs PageModel (Task.18)
2025-09-18 | Frontend development | 4 hours | incomplete | Created Events.cshtml browsing page (Task.26)
2025-09-19 | Frontend development | 3.5 hours | incomplete | Created EventDetails.cshtml page (Task.27)
2025-09-20 | Form integration | 3 hours | incomplete | Integrated login form with backend authentication (Task.18)
2025-09-21 | Testing | 2 hours | incomplete | Tested login page and event browsing pages (Task.18, Task.26)
2025-09-24 | Team meeting | 2 hours | complete | Sprint 1 review and retrospective
2025-09-25 | CSS enhancement | 3 hours | incomplete | Improved responsive design for mobile devices (Task.24)
2025-09-26 | UI components | 3.5 hours | incomplete | Created event card components for browsing (Task.26)
2025-09-27 | Testing | 2 hours | complete | Cross-browser testing (Chrome, Firefox, Safari)
2025-09-28 | Bug fixing | 2 hours | incomplete | Fixed layout issues on event details page (Task.27)
2025-09-29 | Documentation | 1.5 hours | complete | Documented frontend page structure

## Dmitrii Cazacu
Name: Dmitrii Cazacu
Student ID: 40314501
git username: Hildthelsta
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes
2025-09-09 | Team meeting | 2 hours | complete | Sprint 1 kickoff and planning
2025-09-10 | Environment setup | 2 hours | complete | Installed .NET 9.0 SDK and VS Code extensions
2025-09-11 | Repository setup | 1.5 hours | complete | Cloned repo and reviewed project structure
2025-09-12 | Database modeling | 3.5 hours | incomplete | Created Organization model with relationships (Task.12)
2025-09-13 | Code review | 1.5 hours | complete | Reviewed User and Event models for consistency
2025-09-14 | Migration preparation | 2 hours | incomplete | Prepared database schema for initial migration (Task.15)
2025-09-16 | Team meeting | 1.5 hours | complete | Mid-sprint check-in
2025-09-17 | Database migration | 3 hours | incomplete | Created initial EF Core migration (Task.15)
2025-09-18 | Migration testing | 2.5 hours | incomplete | Tested migration and verified table creation (Task.17)
2025-09-19 | Backend development | 3.5 hours | incomplete | Added Organization-User relationship logic (Task.12)
2025-09-20 | Testing | 2.5 hours | incomplete | Tested database relationships and constraints (Task.17)
2025-09-21 | Bug fixing | 2 hours | incomplete | Fixed foreign key constraint issues (Task.15)
2025-09-24 | Team meeting | 2 hours | complete | Sprint 1 review and retrospective
2025-09-25 | Code review | 1.5 hours | incomplete | Reviewed authentication implementation (Task.20)
2025-09-26 | Backend development | 3 hours | incomplete | Created organization query service (Task.34)
2025-09-27 | Testing | 2 hours | incomplete | Tested organization creation and retrieval (Task.34)
2025-09-28 | Documentation | 1.5 hours | complete | Added XML comments to Organization model
2025-09-29 | Migration update | 2 hours | incomplete | Updated migration after schema changes (Task.15)

## Jack Di Spirito
Name: Jack Di Spirito
Student ID:40287812
git username: JackDiSpirito
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes

## Kevin Ung
Name:Kevin Ung
Student ID:40259218
git username: pengukev
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes
2025-09-09 | Team meeting | 2 hours | complete | Sprint 1 kickoff and planning
2025-09-10 | Repository setup | 2 hours | complete | Created GitHub repository with proper structure
2025-09-11 | Database design | 4 hours | incomplete | Designed ERD with all entities and relationships (Task.08)
2025-09-12 | Backend development | 3 hours | incomplete | Set up database schema for Event (Task.01)
2025-09-13 | Database setup | 2.5 hours | incomplete | Configured EF Core and SQLite connection (Task.15)
2025-09-14 | Team coordination | 1.5 hours | complete | Sprint board setup, assigned tasks to members
2025-09-16 | Team meeting | 1.5 hours | complete | Mid-sprint check-in
2025-09-17 | Backend development | 3 hours | incomplete | Created User model with role enum (Task.09)
2025-09-18 | Backend development | 3.5 hours | incomplete | Created Event model with approval status (Task.10)
2025-09-19 | Session configuration | 3 hours | incomplete | Set up session authentication in Program.cs (Task.22)
2025-09-20 | Testing | 2 hours | incomplete | Tested database creation and migrations (Task.17)
2025-09-21 | Code review | 1 hour | incomplete | Reviewed login page implementation (Task.18)
2025-09-24 | Team meeting | 2 hours | complete | Sprint 1 review and retrospective
2025-09-25 | Backend development | 1.5 hours | incomplete | Implemented logout handler (Task.23)
2025-09-26 | Backend development | 2 hours | incomplete | Created Admin table (Task.06)
2025-09-27 | Testing | 3 hours | incomplete | End-to-end testing of authentication flow (Task.20, Task.21)
2025-09-28 | Backend development | 2 hours | incomplete | Created Organizer class/table (Task.05)
2025-09-29 | Sprint prep | 2 hours | complete | Created Sprint 2 issues and backlog

## Nand Patel
Name:Nand Patel
Student ID:40294756
git username: ns-1456
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes
2025-09-09 | Team meeting | 2 hours | complete | Sprint 1 kickoff and planning
2025-09-10 | Environment setup | 2 hours | complete | Installed .NET 9.0 SDK and development tools
2025-09-11 | Repository setup | 2 hours | complete | Cloned repo and explored Razor Pages structure
2025-09-12 | Frontend development | 3.5 hours | incomplete | Created SignupStudent.cshtml page (Task.19)
2025-09-13 | Frontend development | 3.5 hours | incomplete | Created SignupOrganizer.cshtml page (Task.19)
2025-09-14 | UI design | 2 hours | incomplete | Designed signup form layouts with validation (Task.19)
2025-09-16 | Team meeting | 1.5 hours | complete | Mid-sprint check-in
2025-09-17 | Page models | 4 hours | incomplete | Implemented SignupStudent.cshtml.cs PageModel (Task.19)
2025-09-18 | Page models | 4 hours | incomplete | Implemented SignupOrganizer.cshtml.cs PageModel (Task.19)
2025-09-19 | Form validation | 3.5 hours | incomplete | Added client-side and server-side validation (Task.19)
2025-09-20 | Testing | 2.5 hours | incomplete | Tested signup forms with various inputs (Task.19)
2025-09-21 | Bug fixing | 2.5 hours | incomplete | Fixed form submission and validation errors (Task.19)
2025-09-24 | Team meeting | 2 hours | complete | Sprint 1 review and retrospective
2025-09-25 | Backend development | 3 hours | incomplete | Created student table (Task.04)
2025-09-26 | CSS styling | 3.5 hours | incomplete | Styled signup pages with consistent theme (Task.19)
2025-09-27 | Testing | 2 hours | incomplete | Cross-browser testing of signup forms (Task.19)
2025-09-28 | Code review | 1.5 hours | incomplete | Reviewed login page implementation (Task.18)
2025-09-29 | Documentation | 1.5 hours | complete | Documented signup page structure