## Sana Asgharpour
Name: Sana Asgharpour
Student ID: 40244364
git username:
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes

## Salvatore Bruzzese
Name: Salvatore Bruzzese
Student ID: 40112201
git username: sbruzz
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes
2025-10-01 | Team meeting | 2 hours | complete | Sprint 2 planning and task assignment
2025-10-02 | Database modeling | 3 hours | incomplete | Designed Ticket entity model with QR code field (Task.08)
2025-10-03 | Backend development | 4 hours | incomplete | Created Ticket table with EF Core migration (Task.08)
2025-10-04 | Testing | 2 hours | incomplete | Tested ticket table creation and relationships (Task.08)
2025-10-05 | Code review | 1 hour | incomplete | Reviewed event creation backend (Task.12)
2025-10-08 | Team meeting | 1.5 hours | complete | Mid-sprint check-in
2025-10-09 | Backend development | 5 hours | incomplete | Implemented student-ticket relationship logic (Task.10)
2025-10-10 | QR code integration | 4 hours | incomplete | Integrated QRCoder library for ticket generation (Task.10)
2025-10-11 | Backend development | 4 hours | incomplete | Implemented ticket claim handler with capacity check (Task.11)
2025-10-12 | Testing | 2.5 hours | incomplete | End-to-end testing of ticket claiming flow (Task.11)
2025-10-15 | Team meeting | 2 hours | complete | Sprint 2 review and retrospective
2025-10-16 | Backend development | 6 hours | incomplete | Implemented login authentication with BCrypt (Task.30)
2025-10-17 | Session management | 3 hours | incomplete | Configured session-based auth in Program.cs (Task.30)
2025-10-18 | Testing | 2 hours | incomplete | Tested login flow for all user roles (Task.30)
2025-10-19 | Bug fixing | 2 hours | incomplete | Fixed session timeout and redirect issues (Task.30)
2025-10-20 | Code review | 1 hour | incomplete | Reviewed frontend session-based home pages (Task.32)

## Souleymane Camara
Name: Souleymane Camara
Student ID:40183807
git username: mistersuun
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes
2025-10-01 | Team meeting | 2 hours | complete | Sprint 2 planning and task assignment
2025-10-02 | UI design | 3 hours | incomplete | Designed organizer dashboard layout with metric cards (Task.15)
2025-10-03 | Frontend development | 4 hours | incomplete | Created Organizer/Home.cshtml page structure (Task.15)
2025-10-04 | CSS styling | 3.5 hours | incomplete | Implemented custom styling for dashboard cards (Task.15)
2025-10-05 | UI components | 3 hours | incomplete | Built upcoming events timeline component (Task.15)
2025-10-08 | Team meeting | 1.5 hours | complete | Mid-sprint check-in
2025-10-09 | Frontend development | 4 hours | incomplete | Implemented recent activity feed on dashboard (Task.15)
2025-10-10 | Responsive design | 3.5 hours | incomplete | Made dashboard mobile-friendly with breakpoints (Task.15)
2025-10-11 | CSS polish | 2.5 hours | incomplete | Added hover effects and animations to cards (Task.15)
2025-10-12 | Testing | 2 hours | incomplete | Cross-browser testing (Chrome, Firefox, Safari) (Task.15)
2025-10-13 | Bug fixing | 2 hours | incomplete | Fixed layout issues on smaller screens (Task.15)
2025-10-15 | Team meeting | 2 hours | complete | Sprint 2 review and retrospective
2025-10-16 | Code review | 1 hour | incomplete | Reviewed CSV export button UI (Task.17)
2025-10-17 | UI enhancement | 3 hours | incomplete | Styled search and filter components on student home (Task.29)
2025-10-18 | CSS organization | 2.5 hours | incomplete | Refactored CSS into modular stylesheets (Task.29)
2025-10-19 | Documentation | 2 hours | incomplete | Created UI component style guide (Task.29)
2025-10-20 | Sprint prep | 1.5 hours | complete | Prepared Sprint 3 frontend tasks

## Dmitrii Cazacu
Name: Dmitrii Cazacu
Student ID: 40314501
git username: Hildthelsta
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes
2025-10-01 | Team meeting | 2 hours | complete | Sprint 2 planning and task assignment
2025-10-02 | Database analysis | 1.5 hours | incomplete | Reviewed ticket table schema and relationships (Task.08)
2025-10-03 | Backend development | 4 hours | incomplete | Implemented event query service for organizers (Task.14)
2025-10-04 | LINQ optimization | 3 hours | incomplete | Optimized event queries with Include() for eager loading (Task.14)
2025-10-05 | Testing | 2 hours | incomplete | Tested event queries with various filters (Task.14)
2025-10-08 | Team meeting | 1.5 hours | complete | Mid-sprint check-in
2025-10-09 | Service development | 3 hours | incomplete | Created DbCSVCommunicator service class (Task.16)
2025-10-10 | CSV logic | 5 hours | incomplete | Implemented CSV generation from ticket queries (Task.16)
2025-10-11 | CSV formatting | 2 hours | incomplete | Added UTF-8 BOM for Excel compatibility (Task.16)
2025-10-12 | Testing | 2.5 hours | incomplete | Tested CSV export with various data sets (Task.16)
2025-10-13 | Bug fixing | 2 hours | incomplete | Fixed CSV column alignment issues (Task.16)
2025-10-15 | Team meeting | 2 hours | complete | Sprint 2 review and retrospective
2025-10-16 | Code review | 1.5 hours | incomplete | Reviewed login backend implementation (Task.30)
2025-10-17 | Bug fixing | 3 hours | incomplete | Fixed CSV date/time formatting showing ##### in Excel (Task.16)
2025-10-18 | Testing | 2.5 hours | complete | Integration testing for complete organizer workflow
2025-10-19 | Documentation | 1.5 hours | complete | Documented CSV export API and usage
2025-10-20 | Sprint prep | 1.5 hours | complete | Prepared Sprint 3 backend tasks

## Jack Di Spirito
Name: Jack Di Spirito
Student ID:40287812
git username: JackDiSpirito
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes

## Kevin Ung
Name:Kevin Ung
Student ID:40259218
git username: pengukev
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes
2025-10-01 | Team meeting | 2 hours | complete | Sprint 2 planning and task assignment
2025-10-02 | Backend development | 4 hours | incomplete | Created organizer and event relation in database (Task.12)
2025-10-03 | Database migration | 2 hours | incomplete | Added foreign keys for event-organizer relationship (Task.12)
2025-10-04 | Code review | 1 hour | incomplete | Reviewed ticket table creation PR (Task.08)
2025-10-05 | Sprint coordination | 1.5 hours | complete | Updated GitHub issues, assigned remaining tasks
2025-10-08 | Team meeting | 1.5 hours | complete | Mid-sprint check-in, blocker discussion
2025-10-09 | Frontend development | 5 hours | incomplete | Implemented event creation form (Task.13)
2025-10-10 | Testing | 2 hours | incomplete | Tested event creation flow end-to-end (Task.13)
2025-10-11 | Bug fixing | 2.5 hours | incomplete | Fixed validation issues on create event form (Task.13)
2025-10-12 | Documentation | 1 hour | complete | Updated README with new event features
2025-10-15 | Team meeting | 2 hours | complete | Sprint 2 review and retrospective
2025-10-16 | Code review | 2 hours | incomplete | Reviewed CSV export and organizer dashboard (Task.16, Task.15)
2025-10-17 | Testing | 3 hours | incomplete | Integration testing for ticket claiming system (Task.10, Task.11)
2025-10-18 | Sprint planning | 2 hours | complete | Prepared Sprint 3 user stories and tasks
2025-10-19 | GitHub management | 1.5 hours | complete | Closed completed issues, created Sprint 3 issues
2025-10-20 | Documentation | 1.5 hours | complete | Sprint 2 deliverables preparation

## Nand Patel
Name:Nand Patel
Student ID:40294756
git username: ns-1456
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes
2025-10-01 | Team meeting | 2 hours | complete | Sprint 2 planning and task assignment
2025-10-02 | Research | 2 hours | incomplete | Researched session management in Razor Pages (Task.32)
2025-10-03 | Frontend development | 3 hours | incomplete | Started session-based home page routing (Task.32)
2025-10-04 | Page models | 4 hours | incomplete | Implemented role-based redirects in PageModels (Task.32)
2025-10-05 | Testing | 2 hours | incomplete | Tested session handling for different roles (Task.32)
2025-10-08 | Team meeting | 1.5 hours | complete | Mid-sprint check-in
2025-10-09 | Frontend development | 5 hours | incomplete | Created role-specific layouts (Task.32)
2025-10-10 | Session handling | 4 hours | incomplete | Implemented session checks on all protected pages (Task.32)
2025-10-11 | Bug fixing | 2.5 hours | incomplete | Fixed session timeout redirect issues (Task.32)
2025-10-12 | Testing | 2 hours | incomplete | Tested session persistence across pages (Task.32)
2025-10-13 | Code review | 1 hour | incomplete | Reviewed login backend implementation (Task.30)
2025-10-15 | Team meeting | 2 hours | complete | Sprint 2 review and retrospective
2025-10-16 | Frontend development | 2 hours | incomplete | Improved login page UI and functionality (Task.31)
2025-10-17 | Frontend development | 2.5 hours | incomplete | Enhanced login form validation (Task.31)
2025-10-18 | Testing | 3 hours | incomplete | Comprehensive testing of authentication flows (Task.31)
2025-10-19 | Bug fixing | 2 hours | incomplete | Fixed edge cases in session management (Task.32)
2025-10-20 | Documentation | 1.5 hours | complete | Documented session handling patterns