## Salvatore Bruzzese
Name: Salvatore Bruzzese
Student ID: 40112201
git username: sbruzz
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes
2025-10-21 | Team meeting | 2.5 hours | complete | Sprint 3 planning and task assignment
2025-10-22 | Backend development | 4 hours | incomplete | Implemented QR code validation logic (Task.19)
2025-10-23 | Backend development | 5 hours | incomplete | Created ticket redemption tracking system (Task.19)
2025-10-24 | Backend development | 4 hours | incomplete | Implemented file upload handler for QR images (Task.18)
2025-10-25 | Testing | 2.5 hours | incomplete | Tested QR code validation with various formats (Task.19)
2025-10-26 | Bug fixing | 2 hours | incomplete | Fixed QR code decoding issues (Task.19)
2025-10-30 | Team meeting | 1.5 hours | complete | Mid-sprint check-in
2025-11-01 | Backend development | 3.5 hours | incomplete | Enhanced QR scanner with duplicate detection (Task.19)
2025-11-02 | Backend development | 3 hours | incomplete | Implemented ticket redemption status updates (Task.19)
2025-11-03 | Testing | 3 hours | incomplete | Comprehensive testing of QR scanner workflow (Task.19)
2025-11-03 | Code review | 1.5 hours | incomplete | Reviewed admin backend implementations (Task.21, Task.23)
2025-11-04 | Backend development | 3 hours | incomplete | Added QR scanner statistics to organizer dashboard (Task.18)
2025-11-05 | Testing | 3 hours | incomplete | Integration testing of QR scanner with frontend (Task.18)
2025-11-06 | Bug fixing | 2.5 hours | incomplete | Fixed QR code validation edge cases (Task.19)
2025-11-07 | Documentation | 2 hours | incomplete | Documented QR scanner API and usage (Task.18)
2025-11-08 | Code review | 1.5 hours | incomplete | Reviewed frontend QR scanner implementation (Task.20)
2025-11-09 | Team meeting | 2.5 hours | complete | Sprint 3 review and retrospective
2025-11-09 | Testing | 3 hours | incomplete | End-to-end testing of complete QR scanner feature (Task.18, Task.19)
2025-11-10 | Performance optimization | 2.5 hours | incomplete | Optimized QR code processing for large batches (Task.19)
2025-11-10 | Final testing | 2 hours | incomplete | Regression testing of QR scanner features (Task.18, Task.19)

## Souleymane Camara
Name: Souleymane Camara
Student ID:40183807
git username: mistersuun
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes
2025-10-21 | Team meeting | 2.5 hours | complete | Sprint 3 planning and task assignment
2025-10-22 | UI design | 3.5 hours | incomplete | Designed admin dashboard layout (Task.26)
2025-10-23 | Frontend development | 4.5 hours | incomplete | Created Admin/Home.cshtml with analytics cards (Task.26)
2025-10-24 | CSS styling | 4 hours | incomplete | Styled admin dashboard with consistent theme (Task.26)
2025-10-25 | Frontend development | 4 hours | incomplete | Implemented admin user management page (Task.22)
2025-10-26 | UI components | 3 hours | incomplete | Built user approval/rejection UI components (Task.22)
2025-10-30 | Team meeting | 1.5 hours | complete | Mid-sprint check-in
2025-10-31 | Frontend development | 4.5 hours | incomplete | Created admin event moderation page (Task.24)
2025-11-01 | Frontend development | 4 hours | incomplete | Built organization management page (Task.28)
2025-11-02 | UI polish | 3.5 hours | complete | Improved mobile responsiveness across admin pages
2025-11-03 | CSS enhancement | 3 hours | complete | Added loading states and animations
2025-11-03 | Testing | 2 hours | incomplete | Cross-browser testing of admin pages (Task.26)
2025-11-04 | Frontend development | 4 hours | incomplete | Implemented QR scanner frontend interface (Task.20)
2025-11-05 | UI polish | 3.5 hours | incomplete | Enhanced QR scanner UI with file upload (Task.20)
2025-11-06 | UI consistency | 4 hours | complete | Ensured consistent styling across all pages
2025-11-07 | Responsive design | 3.5 hours | complete | Improved mobile responsiveness for all pages
2025-11-08 | Testing | 2.5 hours | complete | Comprehensive UI testing across all user roles
2025-11-09 | Team meeting | 2.5 hours | complete | Sprint 3 review and retrospective
2025-11-09 | UI polish | 3 hours | complete | Final styling refinements across all pages
2025-11-10 | Documentation | 2.5 hours | incomplete | Created frontend architecture documentation (Task.35)
2025-11-10 | Final testing | 2 hours | complete | Comprehensive UI/UX testing
2025-11-10 | Code review | 1.5 hours | complete | Reviewed all frontend implementations

## Dmitrii Cazacu
Name: Dmitrii Cazacu
Student ID: 40314501
git username: Hildthelsta
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes
2025-10-21 | Team meeting | 2.5 hours | complete | Sprint 3 planning and task assignment
2025-10-22 | Backend development | 5 hours | incomplete | Implemented admin analytics aggregation queries (Task.25)
2025-10-23 | Backend development | 4.5 hours | incomplete | Created global statistics calculation service (Task.25)
2025-10-24 | Database optimization | 2.5 hours | incomplete | Added indexes for analytics queries (Task.25)
2025-10-25 | Testing | 2.5 hours | incomplete | Tested analytics calculations with large datasets (Task.25)
2025-10-26 | Code review | 1.5 hours | incomplete | Reviewed QR scanner backend implementation (Task.19)
2025-10-30 | Team meeting | 1.5 hours | complete | Mid-sprint check-in
2025-11-01 | Backend development | 4.5 hours | incomplete | Implemented organization management backend (Task.27)
2025-11-02 | Backend development | 4 hours | incomplete | Created organization-user relationship management (Task.27)
2025-11-03 | Testing | 2.5 hours | incomplete | Tested organization management workflows (Task.27)
2025-11-03 | Performance optimization | 2 hours | incomplete | Optimized organization queries (Task.27)
2025-11-04 | Backend development | 4 hours | incomplete | Enhanced admin analytics with trending data (Task.25)
2025-11-05 | Backend development | 4 hours | incomplete | Implemented event moderation backend logic (Task.23)
2025-11-06 | Testing | 3 hours | incomplete | Integration testing of admin features (Task.23, Task.25)
2025-11-07 | Code review | 1.5 hours | incomplete | Reviewed admin frontend implementations (Task.26)
2025-11-08 | Documentation | 2 hours | incomplete | Documented admin analytics API (Task.25)

## Jack Di Spirito
Name: Jack Di Spirito
Student ID:40287812
git username: JackDiSpirito
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes

## Kevin Ung
Name:Kevin Ung
Student ID:40259218
git username: pengukev
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes
2025-10-21 | Team meeting | 2.5 hours | complete | Sprint 3 planning and task assignment
2025-10-22 | Backend development | 5 hours | incomplete | Implemented admin user approval system (Task.21)
2025-10-23 | Backend development | 4 hours | incomplete | Created event moderation backend logic (Task.23)
2025-10-24 | Database updates | 2 hours | incomplete | Added approval status fields to User model (Task.21)
2025-10-25 | Testing | 2 hours | incomplete | Tested user approval workflow (Task.21)
2025-10-26 | Sprint coordination | 1.5 hours | complete | Updated Sprint 3 backlog and assigned tasks
2025-10-30 | Team meeting | 1.5 hours | complete | Mid-sprint check-in
2025-10-31 | Backend development | 5 hours | incomplete | Implemented global analytics queries (Task.25)
2025-11-01 | Backend development | 4 hours | incomplete | Created organization management backend (Task.27)
2025-11-02 | Testing | 2.5 hours | incomplete | Tested admin analytics calculations (Task.25)
2025-11-03 | Code review | 2 hours | incomplete | Reviewed QR scanner implementation (Task.19)
2025-11-04 | Frontend development | 4 hours | incomplete | Implemented admin home page with analytics (Task.26)
2025-11-05 | Frontend development | 4.5 hours | incomplete | Created admin user management page (Task.22)
2025-11-06 | Testing | 3 hours | incomplete | End-to-end testing of admin features (Task.21, Task.23)
2025-11-07 | Bug fixing | 2 hours | incomplete | Fixed user approval workflow issues (Task.21)
2025-11-08 | Code review | 1.5 hours | incomplete | Reviewed admin dashboard implementations (Task.26)
2025-11-09 | Team meeting | 2.5 hours | complete | Sprint 3 review and retrospective
2025-11-09 | Integration testing | 3 hours | complete | Comprehensive testing of all admin features
2025-11-10 | GitHub workflow | 2 hours | incomplete | Set up automated workflow (Task.33)
2025-11-10 | Documentation | 2 hours | incomplete | Updated architecture documentation (Task.34)
2025-11-10 | Sprint coordination | 2 hours | complete | Final sprint deliverables preparation
2025-11-10 | Code review | 1.5 hours | complete | Final code review of all Sprint 3 features

## Nand Patel
Name:Nand Patel
Student ID:40294756
git username: ns-1456
Date (MM/DD/YYYY) | Task/Activity | Time Spent (hours) | Status | Comments/Notes
2025-10-21 | Team meeting | 2.5 hours | complete | Sprint 3 planning and task assignment
2025-10-22 | Frontend development | 4.5 hours | incomplete | Implemented QR scanner file upload interface (Task.20)
2025-10-23 | Frontend development | 3.5 hours | incomplete | Created QR validation result display (Task.20)
2025-10-24 | Frontend development | 4 hours | incomplete | Built ticket redemption tracking UI (Task.20)
2025-10-25 | UI polish | 2.5 hours | incomplete | Styled QR scanner page with consistent design (Task.20)
2025-10-26 | Testing | 2 hours | incomplete | Tested QR scanner file upload functionality (Task.20)
2025-10-30 | Team meeting | 1.5 hours | complete | Mid-sprint check-in
2025-10-31 | Frontend development | 3.5 hours | incomplete | Enhanced QR scanner with validation feedback (Task.20)
2025-11-01 | UI consistency | 4 hours | complete | Standardized form styling across all pages
2025-11-02 | Responsive design | 3.5 hours | complete | Improved mobile responsiveness for forms
2025-11-03 | UI polish | 3 hours | complete | Added loading states to all forms
2025-11-03 | Testing | 2 hours | incomplete | Cross-browser testing of QR scanner (Task.20)
2025-11-04 | Frontend development | 4 hours | incomplete | Created admin event moderation interface (Task.24)
2025-11-05 | Frontend development | 3.5 hours | incomplete | Implemented event approval/rejection UI (Task.24)
2025-11-06 | UI enhancement | 3 hours | incomplete | Added confirmation modals for admin actions (Task.24)
2025-11-07 | Responsive design | 3.5 hours | complete | Made admin pages mobile-friendly
2025-11-08 | Testing | 2.5 hours | incomplete | Comprehensive testing of admin interfaces (Task.24)
2025-11-09 | Team meeting | 2.5 hours | complete | Sprint 3 review and retrospective
2025-11-09 | UI polish | 3 hours | complete | Final styling refinements across application
2025-11-10 | Testing | 3 hours | complete | End-to-end testing of all user interfaces
2025-11-10 | Documentation | 2 hours | complete | Documented frontend patterns and components
2025-11-10 | Code review | 1.5 hours | complete | Reviewed all frontend implementations